## Road Map
EVENTIFY
|  |  | SPRINT 1 | SPRINT 2 | SPRINT 3
Application Modules | Feature Backlog | Story Points | SPRINT1 - 10/28/2025 | SPRINT2 - 11/18/2025 | SPRINT3 - 12/16/2025
01. Account Management | 01.01 Register User | 5 | X
| 01.02 Login | 3 | X
| 01.03 Reset Password | 3 | X
| 01.04 Manage Profile | 3 | X
| 01.05 Authentication Check | 2 | X
| 01.06 Logout | 1 | X
| 01.07 Accessibility & Language Settings | 3 | X
| 01.08 View User Dashboard | 3 | X |  |  |  |  | 3
02. Event Browsing & Discovery | 02.01 Search by Category/Date/Location | 5 | X
| 02.02 Filter by Price or Type | 3 | X
| 02.03 View Event Details | 2 | X
| 02.04 Save Event to Favorites | 2 | X
| 02.05 Share Event | 2 | X
| 02.06 View Organizer Details | 2 | X |  |  | Story Points | Meaning (Effort & Complexity)
| 02.07 Sort by Popularity or Rating | 2 | X |  |  | 1 Point | 🟩 Very small & simple — clear, minimal logic, no dependency.
03. Organizer Management | 03.01 Create Event | 8 |  | X |  | 2 Points | 🟨 Small & straightforward — simple feature, little backend/UI logic.
| 03.02 Edit Event | 5 |  | X |  | 3 Points | 🟧 Medium complexity — includes multiple components or validations.
| 03.03 Configure Tiers & Capacity | 5 |  | X
| 03.04 Manage Attendee List | 3 |  | X
| 03.05 Generate QR Codes for Check-in | 3 |  | X
| 03.06 Sales Dashboard & Analytics | 5 |  |  | X
| 03.07 Handle Cancellations & Refunds | 5 |  |  | X | 5 Points | 🟦 Large — multi-step flow, integrates with backend, or includes new data model.
| 03.08 Provide Financial Reports | 3 |  |  | X | 8 Points | 🟥 Very large / complex — multiple screens, APIs, or workflows.
04. Ticketing & Payments | 04.01 View Pricing & Seat Availability | 3 |  | X |  | 13 Points | ⛔ Epic / highly uncertain — not fully defined, needs research or split later.
| 04.02 Apply Promo Codes or Discounts | 3 |  | X
| 04.03 Purchase Tickets (Secure Checkout) | 8 |  |  | X
| 04.04 Generate Digital QR Tickets | 3 |  | X
| 04.05 Refund Request | 3 |  |  | X
| 04.06 Cancel Request | 2 |  | X
| 04.07 Payment Gateway Integration | 8 |  |  | X
| 04.08 Download Receipt | 2 |  | X
| 04.09 Revenue Reconciliation & Payout Reports | 5 |  |  | X
05. Notifications and Communications | 05.01 Send Reminders | 3 |  | X
| 05.02 Send SMS Alerts | 3 |  |  | X
| 05.03 Push Notifications | 3 |  | X
| 05.04 Email Confirmations & Cancellations | 3 |  |  | X
| 05.05 Provide Customer Support Responses | 3 |  |  | X
| 05.06 Social Media Integration for Campaigns | 3 |  |  | X
|  | VELOCITY: | 41 | 43 | 49