## Team 1 - Report
Team 1: Jenkins Implementation Planning and Progress Tracking
Admin: | Thilak Narasimhamurthy
Sprint | Task Title | Description | Progress
PREP | Download and Install Java JDK and Jenkins | • Install Java JDK • Install Jenkins | 100%
PREP | Jenkins Configuration | • Install required plugins: • Pipeline Plugin • Git Plugin • GitHub Integration plugin • Create Admin User • Configure global security • Manage and Assign Roles | 100%
PREP | AWS Jenkins Setup | • Create two EC2 Instances: Dev, and QA • Create Key-Pair • Launch Instances | 100%
PREP | Basic Integration on dev and qa server | • Install Git on both server • Install Nginx on Jenkins server • Install NodeJS on Jenkins server | 100%
PREP | Initial Pipeline Setup | • Create a basic Jenkins pipeline job • Develop a simple Jenkinsfile for frontend and backend applications • Execute the pipeline on the Dev EC2 instance | 100%
S1 | Install and Configure Additional Plugins | • Install Blue Ocean, Jira, and Pipeline Utility Steps plugins to improve UI, enable Jira tracking, and enhance scripting. • Configure authentication & API access for smooth integration with Slack and Jira. | 100%
S1 | Build & Dependency Management | • Configure npm clean install (npm ci) for consistent dependencies • Ensure dependency installation on target servers during deployment | 100%
S1 | Automated deployment to Staging Environment | • Configure deployment trigger for staging branch • Implement SSH connection to Dev server • Stop existing PM2 processes gracefully • Clone or update repository with latest code • Start application using PM2 and verify deployment | 100%
S1 | Automated deployment to QA Environment | • Configure deployment trigger for QA branch • Implement SSH connection to QA server • Stop existing PM2 processes gracefully • Clone or update repository with latest code • Start application using PM2 and verify deployment | 100%
S1 | Production deployment with approval Gate | • Configure deployment trigger for main branch • Implement manual approval gate before production deployment • Implement SSH connection to Prod server • Stop existing PM2 processes gracefully • Clone or update repository with latest code • Start application using PM2 and verify deployment | 100%
S1 | PM2 Process management | • Configure PM2 ecosystem file for application management • Implement PM2 process restart and save functionality • Add PM2 status verification after deployment | 100%
S1 | Post-Deployment Actions & Cleanup | • Implement workspace cleanup after pipeline execution • Add success notification messages • Add failure notification messages | 100%
S1 | Security & Error Handling | • Implement SSH agent for secure credential management • Disable StrictHostKeyChecking for automated connections • Add graceful error handling for PM2 stop command | 100%
S2
S2