## Sheet1
Sprint 1: Daily Schedule, Week 7
Tasks | Wednesday -Day 1 | Thursday -Day 2 | Friday -Day 3 | Saturday -Day 4 | Sunday -Day 5 | Monday -Day 6 | Tuesday -Day 7
S1: RCT - Planning (with Crosscuts) | X | X
S1: Supplementary Requirements (Crosscuts, Entitlements in RCT) | X | X
Define User Stories with columns Constraints, Exceptions |  | X | X
S1: Dataflow Diagrams (2) (Logical, S1 scope) | X | X
S1: Start implementing User Stories according to the RoadMap |  |  | X | X
S1: Burndown Chart (in Excel) |  | X | X | X
S1: Jenkins deployment to Dev, QA environments | X
S1: Jenkins - implement Slack notifications | X
Jira: populate User Stories from the RCT, Epics (functional areas) |  |  | X | X
Jira: create RoadMap | X | X
Jira: setup and update Kanban Board |  | X | X