## Road Map
EVENTIFY
|  |  | SPRINT 1 | SPRINT 2 | SPRINT 3
Application Modules | Feature Backlog | Story Points | SPRINT1 - 10/14/2025 | SPRINT2 - 11/04/2025 | SPRINT3 - 12/02/2025
01. Account Management | 01.01 Register User | 5 | X
| 01.02 Login authentication | 3 | X
| 01.03 Reset Password | 2 | X
| 01.04 Manage Profile | 2 | X
| 01.05 View User Dashboard | 0 | X
02. Event Browsing & Discovery | 02.01 Search and filter functionality | 5 | X
| 02.02 View Event Details | 5 | X
| 02.03 Save Event To Favorites | 3 | X |  |  | Story Points | Meaning (Effort & Complexity) | Meaning (Effort & Complexity)
| 02.04 Share Event | 3 |  | X |  | 1 Point | 🟩 Very small & simple — clear, minimal logic, no dependency. | 🟩 Very small & simple — clear, minimal logic, no dependency.
| 02.05 View Organizer Details | 3 |  | X |  | 2 Points | 🟨 Small & straightforward — simple feature, little backend/UI logic. | 🟨 Small & straightforward — simple feature, little backend/UI logic.
03. Ticketing & Payments | 03.01 View Pricing & Seat Availability | 3 |  | X |  | 3 Points | 🟧 Medium complexity — includes multiple components or validations. | 🟧 Medium complexity — includes multiple components or validations.
| 03.02 Purchase Tickets (Promocodes and Discounts) | 5 |  | X |  | 5 Points | 🟦 Large — multi-step flow, integrates with backend, or includes new data model. | 🟦 Large — multi-step flow, integrates with backend, or includes new data model.
| 03.03 Generate Digital QR Tickets | 3 |  | X |  | 8 Points | 🟥 Very large / complex — multiple screens, APIs, or workflows. | 🟥 Very large / complex — multiple screens, APIs, or workflows.
| 03.04 Refund Request | 2 |  | X |  | 13 Points | ⛔ Epic / highly uncertain — not fully defined, needs research or split later. | ⛔ Epic / highly uncertain — not fully defined, needs research or split later.
| 03.05 Payment Gateway Integration | 5 |  |  | X
04. Organizer Management | 04.01 Create and Edit Event | 8 |  | X
| 04.02 Configure Tiers & Capacity | 3 |  | X
| 04.03 Manage Attendee List | 3 |  | X
| 04.04 Generate QR Codes for Check-in | 3 |  |  | X
| 04.05 Sales Dashboard & Analytics | 5 |  |  | X
05. Notifications & Communication | 05.01 Send Reminders and SMS Alerts | 3 |  | X
| 05.02 Push Notifications | 3 |  |  | X
| 05.03 Email Confirmations & Cancellations | 5 |  |  | X
| 05.04 Provide Customer Support Access | 3 |  |  | X
| 05.05 Social Media Integration For Campaigns | 2 |  |  | X
| VELOCITY: |  | 25 | 36 | 26