## Report Example
Team N: Jenkins Implementation Planning and Progress Tracking
Admin: | Admin Name
Sprint | Task Title | Description | Progress
PREP | Download and Install Java JDK and Jenkins | • Install Java JDK • Install Jenkins | 100%
PREP | Jenkins Configuration | • Install required plugins: • Pipeline Plugin • Git Plugin • GitHub Integration plugin • Create Admin User • Configure global security • Manage and Assign Roles | 100%
PREP | AWS Jenkins Setup | • Create two EC2 Instances: Dev, and QA • Create Key-Pair • Launch Instances | 100%
PREP | Basic Integration on dev and qa server | • Install Git on both server • Install Docker on Jenkins server • Install Nginx on Jenkins server • Install NodeJS on Jenkins server | 100%
PREP | Initial Pipeline Setup | • Create a basic Jenkins pipeline job • Develop a simple Jenkinsfile for frontend and backend applications • Execute the pipeline on the Dev EC2 instance | 100%
S1 | Install and Configure Additional Plugins | • Install Blue Ocean, Jira, and Pipeline Utility Steps plugins to improve UI, enable Jira tracking, and enhance scripting. • Configure authentication & API access for smooth integration with Slack and Jira. | 100%
S1 | Slack Notification Enhancements | • Configure Slack Plugin with clear, detailed messages (user stories, env, stagging/production). | 100%
S1 | Deployment Notifications | • Modify Jenkins pipeline to trigger Slack notifications on deployment success/failure. | 100%
S1 | Pipeline Optimization & Cleanup | • Optimize Dev/QA pipelines for faster build times. • Enable automated workspace cleanup post-build to save storage. | 100%
S1 | Staging & Target Environments | • Create separate pipelines for Staging and Target (DEV, QA) with clear notification flows. | 100%
S2 | Enable tasks/pipeline automation
S2 | Jenkins Plugin Configuration | Install required plugins: • Blue Ocean Plugin • Timestamper
S2 | Automatically trigger deployment pipelines once code change has been done on git.
S2 | Initial challenges in automating deployments and sending Jenkins alerts.
S2 | Recognized the need for comprehensive monitoring and logging
S2 | Manage Jenkins plugins carefully and keep them up to date to benefit from new features and bug fixes | • Git Plugins • Git Integration Plugin
S2 | Regularly update Jenkins and its plugins to patch security vulnerabilities
S3 | Implement Role-Based Access Control (RBAC) | We plan to configure the Role-Based Authorization Strategy plugin to define permission levels for admin, developer, and viewer roles, improving access control and security within Jenkins.
S3 | Integrate ESLint with Warnings Next Generation Plugin (updated from SonarQube) | We will integrate ESLint for static code analysis in place of SonarQube. The Warnings Next Generation plugin will be used to display ESLint issues directly in Jenkins UI to ensure front-end code quality and maintainability.
S3 | Set Up OWASP Dependency-Check | As part of securing our CI pipeline, we will configure the OWASP Dependency-Check plugin to scan third-party libraries for known vulnerabilities and generate alerts during build time
S3 | Add Manual Approval for Production Deployment | We plan to introduce a manual approval gate using the Promoted Builds plugin or Jenkins input step before deploying to QA. This allows us to verify readiness and prevents accidental releases.
S3 | Integrate JMeter for Performance Testing | JMeter scripts will be added to evaluate API performance. Test results will be visualized in Jenkins post-build to ensure application responsiveness and catch regressions early.
S3 | Retry Failed Stages Automatically | To make the pipeline more resilient, we plan to implement retry logic for unstable steps like Docker login or ECR push to reduce build failures caused by temporary issues.
S3 | Publish Test and Coverage Reports | We will configure Jenkins to collect and display JUnit test results and code coverage reports, allowing the team to quickly verify the quality and reliability of each build.
S3 | Integrate Jenkins with Grafana via Prometheus | We plan to expose Jenkins job metrics using the Prometheus plugin and visualize real-time build stats, trends, and failure rates using Grafana dashboards.

## Team 1 - Report
Team 1: Jenkins Implementation Planning and Progress Tracking
Admin: | Thilak Narasimhamurthy
Sprint | Task Title | Description | Progress
PREP | Download and Install Java JDK and Jenkins | • Install Java JDK • Install Jenkins | 100%
PREP | Jenkins Configuration | • Install required plugins: • Pipeline Plugin • Git Plugin • GitHub Integration plugin • Create Admin User • Configure global security • Manage and Assign Roles | 100%
PREP | AWS Jenkins Setup | • Create two EC2 Instances: Dev, and QA • Create Key-Pair • Launch Instances | 100%
PREP | Basic Integration on dev and qa server | • Install Git on both server • Install Nginx on Jenkins server • Install NodeJS on Jenkins server | 100%
PREP | Initial Pipeline Setup | • Create a basic Jenkins pipeline job • Develop a simple Jenkinsfile for frontend and backend applications • Execute the pipeline on the Dev EC2 instance | 100%
S1 | Install and Configure Additional Plugins | • Install Blue Ocean, Jira, and Pipeline Utility Steps plugins to improve UI, enable Jira tracking, and enhance scripting. • Configure authentication & API access for smooth integration with Slack and Jira. | 100%
S1 | Build & Dependency Management | Configure npm clean install (npm ci) for consistent dependencies Ensure dependency installation on target servers during deployment | 100%
S1 | Automated deployment to Staging Environment | Configure deployment trigger for staging branch Implement SSH connection to Dev server Stop existing PM2 processes gracefully Clone or update repository with latest code Start application using PM2 and verify deployment | 100%
S1 | Automated deployment to QA Environment | Configure deployment trigger for QA branch Implement SSH connection to QA server Stop existing PM2 processes gracefully Clone or update repository with latest code Start application using PM2 and verify deployment | 100%
S1 | Production deployment with approval Gate | Configure deployment trigger for main branch Implement manual approval gate before production deployment Implement SSH connection to Prod server Stop existing PM2 processes gracefully Clone or update repository with latest code Start application using PM2 and verify deployment | 100%
S1 | PM2 Process management | Configure PM2 ecosystem file for application management Implement PM2 process restart and save functionality Add PM2 status verification after deployment | 100%
S1 | Post-Deployment Actions & Cleanup | Implement workspace cleanup after pipeline execution Add success notification messages Add failure notification messages | 100%
S1 | Slack notification to all environments | Install slack plugin Connect Jenkins to Slack and test connection Post notification to slack channel after every build | 100%
S1 | Provide Access to teammates role wise | Install Role-based strategy plugin Add roles and environments access Create users and share with teammates to test accessibility | 100%
S2 | Email Notification Setup and Configuration | Install Email Extension Plugin Configure SMTP server settings (Gmail/Outlook/Corporate) Set up default email recipients list Configure global email credentials | 100%
S2 | Email Template and Content Configuration | Configure email templates for success notifications Configure email templates for failure notifications Configure email triggers (on build start, success, failure, unstable) Add build logs and artifact links in email body Customize email subject line with build status and branch info | 100%
S2 | Environment Deployment and Email Testing | Add email notification to Dev environment deployment Add email notification to QA environment deployment Add email notification to Prod environment deployment Set up email notification for manual approval requests Test email delivery to all team members Verify email notifications across all environments | 100%